## MVP
Product Initiative | Module / Area | Feature / Deliverable | User Story | Acceptance Criteria | Business Objective | Persona / Segment | Priority | Status | Cycle | Dependencies | Notes | Trello Link | PM Notes
Auth & Access | Sign Up | Registration page (name, email, phone, password, repeat password, consents) | As a Curo user, I want to sign up with my email/password, so that I have greater control over my account | - Required fields validated with inline hints - Passwords must match - ToS/Privacy consent required - OTP phone verification can follow | Increase activation | All | Must-Have | In Progress | Now | Auth service - Twilio/Email integration) | Basic registration is present. Need to add the following: - ToS/Privacy consent - Email verification - Phone verification by OTP | https://trello.com/c/H5PxjkMd/4-auth-epic-01-email-password-registration | Sprint 1
Auth & Access | Sign Up | Registration page (Google SSO to collect name, email, phone) | As a Curo user, I want to sign up with my Google account, so that I can speed up the sign up process | - Google SSO fetches all required info (name, email, phone) - Clear error message if user doesn't have valid Google account | Increase activation | All | Should-Have | In Progress | Now | Google SSO service | Not present | https://trello.com/c/H5PxjkMd/4-auth-epic-01-email-password-registration | Sprint 1
Auth & Access | Login | Login page | As a Curo user, I want to login quickly, so that I can start sending and receiving payments | - Email/phone + password - Google SSO - Remember me option - Error states for wrong creds, lockout | Engagement/Adoption | All | Must-Have | In Progress | Now | Auth service | Login screen with remember me check and validations are present, need to add the following: - Currently, only email is required with a password to log in; need to include a phone number as another option. - Google SSO | https://trello.com/c/fGx2JIxe/12-auth-epic-02-login-session-management | Sprint 1
Auth & Access | Password Reset | Forgot Password / Reset flow | As a Curo user, I want to reset my password by email, so that I can get back into my account quickly | - Request with email or phone - Tokened reset page with expiry - Rate limiting + confirmation | Reduce support load | All | Must-Have | In Progress | Now | Auth service - Email integration | Forget password with email input is present, need to add phone number as an option for password recovery | https://trello.com/c/ULUPJWFF/17-auth-epic-03-forgot-password-password-reset | Sprint 1
Activation & Onboarding | KYC Stepper | Limits-based KYC page/stepper | As a Curo user, I want simple identity steps that scale only if needed, so that I can verify my identity. | - Light tier: phone OTP + name + address - Escalate to DOB/SSN when limits require - Progress indicator & why-we-ask | Increase Adoption | All | Must-Have | Planned | Next | KYC vendor | Implemented with Plaid's step Wizard to submit details required in every step | https://trello.com/c/0lPyocBD/22-activation-onboarding-kyc-stepper-limits-based-identity-verification-plaid-tbd-vendor | Sprint 2
Activation & Onboarding | Home / Dashboard | Intent-first home page | As a Curo user I want big clear actions to send or print a check, so that I can send payments quickly. | - Tiles: Send a Check, Print a QR Check, Call to Set Up - Recent activity list (3 items) - Accessible large buttons | Increase Adoption | All | Must-Have | Planned | Next | Home | Dashboard Present with limited and basic information | https://trello.com/c/y2GduWKE/23-activation-onboarding-intent-first-home-page-send-print-check-tiles-recent-activity | Sprint 2
Billing & Payments | Payment Methods | Add Bank Account / Payment Method | As a Curo user, I want to add a bank account or card as a payment method, so that I can fund or receive payments. | Support bank link via Plaid (instant) and micro-deposits (fallback). For cards, support debit/prepaid only as funding (no credit); require AVS/CVV. Mask sensitive details; show last-4 + bank name. Confirm default method selection; display fees/speed impacts before save. | Adoption & Usability | All | Must Have | Planned | Next |  | Using Plaid Authorization to connect bank accounts to the user's profile. Here, the user can follow a wizard hosted by Plaid to add and connect bank account. There is no user flow present for fallback, microdeposits and Cards. | https://trello.com/c/hpEmPLUe/24-billing-pm-epic-04-add-manage-payment-methods | Sprint 2
Billing & Payments | Payment Methods | Edit Payment Method | As a Curo user, I want to edit nicknames and default settings for my payment methods, so that I can control which method is used by default. | Allow nickname, default toggle, and notification preferences; block edits to tokenized PAN and bank identifiers; audit trail on changes. | Adoption & Usability | All | Must Have | Planned | Next |  | Users can edit bank accounts, but only with limited information, such as nickname and status. | https://trello.com/c/hpEmPLUe/24-billing-pm-epic-04-add-manage-payment-methods | Sprint 2
Billing & Payments | Payment Methods | Disable / Remove Payment Method | As a Curo user, I want to disable or remove a payment method, so that I can prevent future use of an old or compromised method. | If active obligations exist (recurring, pending payouts), show blockers and next steps; soft-disable with clear state; hard-delete when safe; log action to audit. | Adoption & Usability | All | Must Have | Planned | Later |  | User can only delete bank accounts. | https://trello.com/c/hpEmPLUe/24-billing-pm-epic-04-add-manage-payment-methods | Sprint 2
Billing & Payments | Payment Methods | Verification Status & Errors | As a Curo user, I want to see verification status and resolve errors, so that I can complete setup without contacting support. | Status chips: Verified, Pending (micro-deposits), Action Needed; inline guides for mismatch/NSF; retry flows; support escalation link. | Adoption & Usability | All | Must Have | Planned | Later |  | Not present | https://trello.com/c/hpEmPLUe/24-billing-pm-epic-04-add-manage-payment-methods | Sprint 2
Directory & Payees | Payees | Add Payee | As a Curo user, I want to add a payee with name and contact, so that I can send them a payment or request. | Collect name + email/phone; optional address; validate duplicates; allow tags (landlord, roommate, vendor); create contact card. | Adoption & Usability | All | Must Have | Planned | Later
Directory & Payees | Payees | Edit Payee | As a Curo user, I want to update a payee’s contact or preferences, so that payments reach the right destination. | Editable fields: contact methods, memo defaults; approval required for risky changes (e.g., payout method); maintain history of changes. | Adoption & Usability | All | Must Have | Planned | Later
Directory & Payees | Payees | Delete / Merge Payee | As a Curo user, I want to delete or merge duplicate payees, so that my directory stays clean. | If payee has historical transactions, require confirmation and keep read-only record; merge flow resolves duplicates safely; prevent deletion when payouts pending. | Adoption & Usability | All | Must Have | Planned | Later
Directory & Payees | Payees | Payee List, Search & Filters | As a Curo user, I want to quickly find payees, so that I can send or request without delay. | Search by name, tag, recent; infinite scroll or pagination; recent activity indicators; accessibility compliant. | Adoption & Usability | All | Must Have | Planned | Later
Directory & Payees | Payees | Payee Verification & Trust Signals | As a Curo user, I want to see whether a payee is verified, so that I can avoid sending to the wrong person. | Show badges for Verified identity and prior successful receipts; warning for unverified; explain benefits and how to verify. | Adoption & Usability | All | Should Have | Planned | Later
Money Movement | Create Check Wizard | Multi-step wizard page | As a Curo user, I want a guided flow to send or print a check, so that I don't make any mistakes. | - Steps: Amount → Payee (modal) → Delivery → Funding → Review - Validation each step; back/next persists data - Works with Senior Mode | Engagement/Adoption | All | Must-Have | Planned | Later | Wizard
Money Movement | Add Payee Modal | Add Payee modal/page | As a Curo user, I want to add a payee with minimal fields, so that I can send them money for bills or birthday presents. | - Requires name + (email or phone or address) - Inline validation - Saved to contacts | Engagement/Adoption | All | Must-Have | Planned | Later | Contacts
Money Movement | Bank Link Modal | Embedded Plaid Link modal | As a Curo user, I want to link my bank inline if I choose, so that I can send the money right away. | - Launch Plaid Link without leaving wizard - Skip allowed for Print QR - Fallback micro-deposits | Shorten TTFT | All | Must-Have | Planned | Later | Plaid
Money Movement | Payments > Recurring | Recurring Schedules | As Marco, I want my split or disbursements to recur on a set cadence automatically, so that I don’t set it up again. | Recurring rule with due day, grace window, auto-reminders; skip/adjust one cycle; proration for move-ins/outs. | Engagement & Usability | Marco | Could-Have | Planned | Later |  | Recurring rules: - Schedule definition (frequency, start date, end date) - Due day configuration (e.g., "1st of month", "every 15th") - Grace period logic (X days after due date) - Recurrence patterns (monthly, bi-weekly, custom intervals) Notification System: Trigger points: - N days before due date (configurable?) - On due date - During grace period - Post grace period (what happens?) Edge cases to handle: - Skip removes payment obligation OR defers it? - Adjust changes amount OR changes date? - Does skipping affect future cycles? - What's the deadline to skip/adjust? Proration Logic - Move-in mid-cycle: pro-rate first payment - Move-out mid-cycle: pro-rate final payment - Do both scenarios use the same calculation method? Critical unknowns: Proration calculation method (daily? 30-day month? actual days?) Handling partial month scenarios Minimum proration amount/threshold? Does proration create a one-time payment or adjust the recurring schedule? What's Missing from the User Story Error handling: What happens when payment fails? Cancellation flow: How does Marco stop the recurrence? Historical tracking: Audit log requirements? Multi-party scenarios: Do all split parties get notified? Payment method: Can Marco change payment method mid-recurrence? Retroactive changes: Can past cycles be modified?
Money Movement | Saved Flows | Repeat last payment / favorites (grandson, utilities) | As a Curo user, I want to repeat common payments quickly, so I don't need to go through the whole flow each time. | - Save any completed flow as favorite - One-tap repeat with editable amount/date - Tracks usage for suggestions | Retention; time-to-value | All | Could-Have | Planned | Later | —
Payee Experience | Claim e‑Check (Guest) | Guest claim page | As a Curo users' payee, I want to claim without creating an account, so I can get my money right away. | - Verify email/phone - Choose payout (Plaid or manual routing) - Confirmation page; invitation to sign up | Increase claim completion | All | Must-Have | Planned | Later | Claim Flow
Payee Experience | Payout Options | ACH credit (default), optional debit push | As a Curo users' payee, I want money deposited into my bank quickly, so that I can access my funds. | - ACH credit via provider - If eligible, instant debit push - Show ETA and fees clearly | Trust; satisfaction | All | Should-Have | Planned | Later | Payments partner
Payee Experience | My e‑Checks (Recipient) | Recipient portal page | As a recipient, I want to see checks I’ve received (if I sign up), so that I make sure I didn't miss any payments. | - List of received checks - Payout status - Basic filters | Satisfaction; stickiness | All | Could-Have | Planned | Later | Recipient Portal
Settings & Support | Settings | Profile & Security page | As a Curo user, I want to adjust my profile, recovery, so that my account is secure. | - Contact info and recovery options - Optional 2FA (could) | Accessibility & security | All | Should-Have | Planned | Later | Settings
Auth & Access | Verify Phone (OTP) | OTP verification page | As a Curo user, I want to verify my phone via a code, so that I can ensure my account is secure and I can send payments via SMS | - Receive OTP via SMS/voice - 6‑digit entry with resend timer - Success leads back to flow | Trust & security | All | Must-Have | Planned | Later | Messaging - Twilio | Not present | https://trello.com/c/H5PxjkMd/4-auth-epic-01-email-password-registration | Moving to later sprint
Notifications & Trust | Status Updates | Sender notifications: delivered, claimed, deposited | As a Curo user, I want to know when my check arrives and is deposited, so that I am kept in the loop. | - Push/email/SMS status toggles - Timeline view in receipt thread - Retry guidance on failure | Usability & reduce support load | All | Must-Have | Planned | Later | Messaging provider
Notifications & Trust | Payee Delivery (Email/SMS) | Email & SMS delivery with clear Claim button | As a Curo user, I want my payee to receive a simple message they trust. | - Branded email/SMS via provider - Claim button deep-links to secure claim - Anti-phish tips shown on first open | Increase claim completion | All | Must-Have | Planned | Later | SendGrid/Twilio
Notifications & Trust | Sent Checks / Timeline | Activity Timeline (Request → Approvals → Delivery → Claim → Deposit) | As Marco, I want a clear timeline for each payment, so that I can see who did what and when. | Step-by-step timeline with timestamps & actors • Links to approval decisions and receipts • Exportable as PDF | Transparency; faster resolution | Marco | Must-Have | Planned | Later | — | View that shows a timeline of transactions, including actor, action, and status, along with timestamps.
Notifications & Trust | Payee Verification | Payee Verification Status (attested/verified) | As Marco, I want to see payee verification status, so that I can reduce fraud and payment exceptions. | Status badge on payee and during send • Verification method & date recorded • Warning if risky/unverified | Lower exceptions & fraud risk | Marco | Should-Have | Planned | Later | — | —
Controls & Assurance | Groups > Payee Groups & Roles | Household (Payee Group) & Roles | As Marco, I want to set roles and permissions for the house, so that I control who approves payouts or changes splits. | Create 'Household/Trustee' group; roles: Owner, Co‑payer, Viewer. Optional approval thresholds for payout or changes; activity audit trail per action. | Usability & Engagement | Marco | Should-Have | Planned | Later
Controls & Assurance | Delegated Access | Delegate Invite & Permission Model | As an account owner, I want to invite a trustee or caregiver to help manage my account with specific permissions, so they can help me without having full control. |  | Adoption & Engagement | All | Must-Have | Planned | Later |  | - Single-account model: every person has their own primary account, no special “trustee dashboard”. - Owner can invite delegate by email/phone and select permissions (e.g., create checks, approve checks, manage payees, manage bank accounts). - Delegates keep their own login but gain scoped access to the owner’s account. - All invites/acceptances are explicit and auditable. - Wire Trustee/delegate permissions into Money Movement (who can create/modify recurring schedules for another account)
Controls & Assurance | Settings > Limits & Approvals | Shared Approvals & Limits | As Marco, I want shared approvals on large payouts, so that everyone signs off on big changes. | Configure $ thresholds and co‑approval requirement; notifications to approvers; timeout & fallback rules. | Usability & Engagement | Marco | Should-Have | Planned | Later |  | - Per-delegate thresholds (e.g., max per check, per day, per week). - Actions under threshold: delegate can execute directly. - Actions above threshold: create approval request to owner (or designated approver). - Owner gets in-app + email notification to approve/decline quickly. - Clear UX for delegates when an action “requires owner approval”.
Controls & Assurance | Vendors / Payees | Trusted Vendor Directory | As a Marco, I want to save trusted vendors (pharmacy, utilities, aides), so that payouts are fast and consistent. | Create/edit vendors with type (healthcare, utility, caregiver), contact, and preferred payout method; quick‑select in send flow; de‑duplication and merge. | Usability & Engagement | Marco | Should-Have | Planned | Later | Directory service, Payout method registry | Optionally mark vendor as medical expense for export.
Controls & Assurance | Approvals | Approvals Center (Pending & History) | As Marco, I want a central place to review and take action on pending approvals, so that I can keep payments moving without confusion. | Shows pending / approved / rejected with filters • Approve/Reject with reason • All actions audit-logged • Bulk approvals for recurring sequences | Reduce delays & disputes | Marco | Must-Have | Planned | Later | — | Surface from notifications and timeline; plain-English actions
Controls & Assurance | Approvals | Emergency Override (requires two trustees) | As Marco, I want an emergency override that requires two trustees, so that I can handle urgent payments safely. | Override visible only on blocked items • Requires two approvers • Reason & expiry required • Prominently logged | Balance speed & safety | Marco | Could-Have | Planned | Later | — | —
Controls & Assurance | Settings > Limits & Approvals | Threshold Templates (e.g., ≥$500 requires 2 approvals) | As Marco, I want presets for common approval thresholds, so that I can set up controls quickly and consistently. | Default templates provided and editable • Apply per-account or per-payee • Conflict warnings shown | Speed setup; reduce configuration errors | Marco | Must-Have | Planned |  | Approvals service | —
Controls & Assurance | Settings > Limits & Approvals | Freeze/Unfreeze Outflows (with reason) | As Marco, I want to freeze payments temporarily, so that I can prevent spend during reviews or emergencies. | Toggle freeze with reason & optional expiry • Blocks send/print until unfrozen • Logged to audit trail | Prevent misuse; risk mitigation | Marco | Should-Have | Planned |  | — | —
Controls & Assurance | Disputes | Dispute Intake & Guided Resolution | As Marco, I want a guided way to submit and track disputes, so that I can resolve issues without guesswork. | Intake form with categories • Evidence upload • Status updates • Linked to impacted transaction • Escalation path | Reduce support load; faster resolution | Marco | Could-Have | Planned |  | — | —
Controls & Assurance | Groups > Roles | Viewer/Observer Role (read-only) | As Marco, I want to grant view-only access to family members, so that they can see activity without changing anything. | Invite by email • No payment abilities • Can view receipts/ledger & timelines • Revocable; audit entry created | Family alignment; transparency | Marco | Must-Have | Planned |  | — | —
System & Legal | Legal Pages | Terms, Privacy, ACH auth, E‑sign disclosure | As a Curo admin, I need transparent legal terms, so that we are protecting the business. | - Linked in footer and during consent - Versioned documents - Accessible format | Compliance | All | Must-Have | Planned |  | —
System & Legal | Error & Empty States | Error/empty states & maintenance banner | As a Curo, I need clear guidance when something goes wrong, so I know how to rectify the situation. | - 403/404/500 with guidance - Empty lists with CTAs - Outage banner capability | Usability | All | Must-Have | Planned |  | System UI
Records | Receipts & Ledger | Audit Export Pack (CSV/PDF bundle for attorney/CPA) | As Marco, I want an audit-ready export of transactions and approvals, so that I can share accurate records with our attorney and CPA. | Export includes transactions, approvals, receipts • Selectable date ranges and payees • Generates a ZIP with PDFs + CSV | Reduce admin time; improve compliance | Marco | Should-Have | Planned |  | Ledger & Receipts service | Comprehensive dos and uncleared points on this module: Audit Export Pack (CSV/PDF bundle for attorney/CPA)
Account Delegation & Trustees | UX & Navigation | Account Switcher & Active Context Banner | As a delegate (trustee or caregiver), I want an easy way to switch between my own account and other accounts I manage, so I always know on whose behalf I’m acting. |  |  | All | Must-Have | Planned |  |  | - Slack-style account/workspace switcher in profile dropdown or top nav. - List: “My Account” + any delegated accounts with owner name + role (e.g., “Acting for Evelyn – Trustee”). - Visible banner/indicator: “Acting on behalf of [Owner Name] – permissions: …”. - No password sharing; server-side session context switch only.
Account Delegation & Trustees | Security & Auditing | Delegated Action Audit Trail & Notifications | As Curo, I want a clear audit trail of all delegated actions, so we can support compliance, dispute resolution, and security investigations. |  | Adoption | All | Should-Have | Planned |  |  | - Data model: relationship table (account_id, delegate_user_id, permissions[], thresholds, status, invited_by, created_at). - Log: invites, accept/decline, permission changes, threshold changes, and all actions taken by delegates (who acted, on which account, what action, timestamp, IP/device). - Email/notification flows for invites, approvals, critical changes.
Analytics | Event Taxonomy v1 | Events for activation and claim funnels (persona-tagged) | As a PM, I want to measure where users succeeds or drops, so that I can enhance the product. | - Track: tile click, KYC start/complete, Plaid link, print PDF, send, claim, payout - Include persona tag and assist flag | Data-driven iteration | All | Must-Have | Planned |  | CDP/Amplitude/Mixpanel
Analytics | Event Taxonomy v1 | Instrumentation & A/B Testing | As a PM, I want analytics on intent selection and first-run completion, so that I can optimize activation without hurting conversion. | Track: registration→intent selection, micro-setup steps, TTFT, D7 activation by intent. A/B: compare 'Skip for now' prominence, tile copy, and micro-setup length. | Adoption / Activation | All | Must Have | Planned |  |  | Define guardrail metrics: registration completion rate, verification completion rate.
Settings & Support | Help Center | Support / How it works page | As a Curo user, I want to reference FAQs, so that I can troubleshoot on my own | - FAQ - “How it works” explainer - Call us link | Build trust; reduce tickets | All | Should-Have | Planned | Backlog | Help
Human‑Assist & Accessibility | Agent Console | Agents can create/send on behalf of user (with consent) | As an Admin, I want to help Curo users complete account setup, so that they can start sending checks | - Consent captured and logged - Draft restored to user account - Actions are audited | Reduce abandonment | Admin | Could-Have | Planned | Backlog | Auth; Audit logging
Human‑Assist & Accessibility | Concierge “Call to Complete” | Sticky call-to-complete on every critical step | As a Curo user, I want to complete by phone if I get stuck, so that I don't make any mistakes. | - Button opens call or schedules callback - Passes context (screen + draft data) to agent console - Track assist outcomes | Increase assisted activation | All | Nice-to-Have | Planned | Backlog | Telephony; Agent console
Security & Recovery | Account Recovery | Phone-based recovery and PIN option | As a Curo user, I want an easy way to get back into my account, so that I can keep using Curo. | - Recovery via phone + DOB last 2 digits - Optional account PIN - Rate limiting & alerts | Reduce churn & support tickets | All | Nice-to-Have | Planned | Backlog | KYC vendor

## Future (hidden)
Product Initiative | Module / Area | Feature / Deliverable | User Story | Acceptance Criteria | Business Objective | Persona / Segment | Priority | Dependencies | Notes | Trello Link | PM Notes
First-Run Personalization | Onboarding > First-Run | Intent Picker (Post-Registration) | As a new user, I want to choose how I’ll use Curo first, so that my home and checklist match my immediate goal. | Appears immediately after account creation/verify (not in the registration form). Requires selecting one primary intent (Send, Print, Split, Caregiving, Receive) with 'Skip for now' available. Accessible: large buttons, clear copy, keyboard and screen-reader friendly. | Adoption / Activation | All | Nice to have |  | Do not hard-disable other features; this only prioritizes navigation and checklists. |  | Focus on Caregiver/Trusts
First-Run Personalization | Onboarding > Micro-Setup | Intent Micro-Setup | As a new user, I want a short setup tailored to my chosen intent, so that I can complete my first task quickly. | Send: add payee, amount, optional memo; link bank inline or defer; show fee/speed before confirm. Split: house name, roommates, amount, due date. Caregiving: beneficiary name, role (proof later). Print: printer test + sample PDF. Receive: phone/SMS verify. Each micro-setup ≤2 screens; can be skipped. | Adoption / Activation | All | Nice to have |  | Progressive KYC prompts only when required for limits/speeds.
First-Run Personalization | Home > Personalization | Personalized Home & Checklist | As a new user, I want a home screen tailored to my intent, so that the next steps are obvious. | Reorders nav to surface relevant modules; shows a 3–5 item checklist; includes 'Change how I use Curo' link. No features are removed—only de-emphasized. | Adoption / Activation | All | Nice to have |  | Instrument attach rates for non-selected modules to ensure discoverability.
First-Run Personalization | Settings > Preferences | Change How I Use Curo | As a user, I want to change or add intents later, so that Curo stays aligned with my evolving needs. | Available under Settings; add/remove intents in ≤2 clicks; updates home tiles/checklist instantly; no data loss. | Adoption / Activation | All | Nice to have |  | Need more details to understand use of this user flow
Activation & Onboarding | Profile & Preferences | Profile stub (Senior Mode, contact prefs) | As Evelyn, I want to turn on Senior Mode easily, so that the UI is more accessible to my needs. | - Toggle Senior Mode from profile and first-run - Save contact prefs (email/SMS) - Persisted to user profile | Accessibility | Evelyn | Nice to have | User Profile | Need to make UI Experience for Senior Mode
Activation & Onboarding | Onboarding > Intent Wizard | Intent Wizard: Split Rent/Utilities | As Jasmine or Marco who fronts rental and utility payments, I want to start from a 'Split bill' wizard, so that I can set up the house, amount, and due dates in one pass. | Wizard captures house name, address (optional), roommates (names, emails/phones), total amount, split method (equal/custom), and due date. Creates a Payee Group and a recurring schedule stub; invites roommates via SMS/email with join link. Success screen shows first cycle preview and options: request now, schedule, or attach landlord payee. | Adoption & Usability | Jasmine | Must-Have |  | Not present
Money Movement | Card Load | Card Load to Check (Debit/Prepaid) | As James, I want to load funds from a debit or prepaid card to generate a Curo check, so that I can pay someone even if I don’t have a bank account. | Supports Visa/Mastercard debit and network-branded prepaid; AVS/CVV required; risk limits by amount/velocity. Clear fee & speed disclosure before confirm; post-auth generates QR-backed check artifact and receipt. Handle declines with actionable reasons; store partial PAN tokens only per PCI; no raw card storage. | Adoption & Usability | James | Should-Have |  | Initial scope = debit/prepaid; credit cards excluded for risk. Consider wallet top-up later.
Money Movement | Split Request & Collection | Payments > Split & Settle | As Jasmine, I want to request each roommate’s share and track who’s paid, so that I don’t chase people manually. | Create per-roommate requests with payment links; support partial payments and over/under adjustments. Real-time ledger shows Paid / Pending / Late; one-tap remind; fees/speed disclosed for each roommate." | Adoption & Usability | Jasmine | Must-Have
Money Movement | Payments > Speed Tiers | Instant / Next‑Day Settlement Options | As Jasmine, I want instant or next‑day settlement to the landlord, so that I can avoid late fees. | Offer speed tiers with transparent fees; surface ETA pre-confirm; show proof of certified funds on receipt. If instant not available, fallback to next‑day with clear cut-off times." | Adoption & Usability | Jasmine | Should-Have |  | Fee willingness modest; ensure clean disclosure.
Money Movement | Payments > Landlord Payee | Landlord Payee & Single‑Pay Out | As Jasmine, I want to pay the landlord once after collecting shares, so that I don’t front the full amount. | When enough shares are collected (threshold), allow one-tap payout to the landlord. Generate a receipt with identity/funds attestation; support QR-backed artifact if landlord requires paper." | Adoption & Usability | Jasmine | Must-Have
Money Movement | Fund-on-Claim | Fund-on-claim option with sensible limits | As Evelyn, I want to send or print without linking a bank right away, so that I can still send money to my grandson. | - If no bank linked, mark check as “fund-on-claim” - Limit amount and frequency; cooldown windows - Recipient sees certification path on claim | Adoption | Evelyn | Must-Have | Risk engine; Certification svc
Paper↔Digital Bridge | QR Check Generator | Printable QR check (PDF) with clear deposit instructions | As Evelyn or James, I want to print a secure check with a QR so I can mail it. | - PDF renders bank/payee/amount with QR payload - No routing/account printed; QR only - Mail-ready page format option | Adoption & Usability | Evelyn, James | Must-Have | PDF service; QR signing
Paper↔Digital Bridge | Retail Print | Retail print/pickup (pilot) | As Evelyn or James, I want to pick up my printed check nearby, so that I have another option if I can't print it. | - Generate secure pickup code - Partner print location receives file - Pickup logged; receipt stored | Adoption & Engagement | Evelyn, James | Nice-to-have | Retail print partner
Paper↔Digital Bridge | Mail Pack | Mail-friendly cover sheet + instructions | As Evelyn or James, I want clear mailing instructions, so that I can reduce mistakes. | - Generates cover sheet with to/from and QR tips - Shows expected delivery times - Save/print options | Reduce support tickets | Evelyn, James | Should-Have | — | Marketing/Branding, need copy & design
Notifications & Trust | Notifications > Reminders | Smart Reminders & Dunning | As Jasmine, I want automatic reminders and polite nudges, so that I spend less time chasing payments. | "Schedule reminder cadence: due‑7, due‑1, due‑day, late‑3; channels: SMS/email; friendly copy; opt-out controls. Escalation: group message to all after X days late; logs all reminders in activity." | Usability / Retention | Jasmine | Could-Have | Messaging provider